## Slide 1: 2023 CDBG Compliance Workshop
Administrator Training
November 16, 2023

## Slide 2: Awards and Contracting
2023 awards are imminent
  Will fund most applications
  Parks are being funded with CDBG-CV funds
All awardees must complete and submit the following forms before the contract is sent by ECD
  Grant Payment Setup Form
  Signature Authorization Form (Update anytime personnel changes)
Information submitted must match what is in Edison
Must submit a new direct deposit form for new accounts

## Slide 3: Title VI Compliance
Title VI compliance and training always occurs after awards
Title VI Survey and non-discrimination policy are required for new grantees
All grantees with open grants must complete Title VI training annually
Select the “Audit & Title VI” tab on our Grant Administration page to find the Title VI training and to submit Title VI documents

## Slide 4: Audit Reviews and Risk Assessments
Audit reviews and risk assessments will begin after awards are issued.
These affect the likelihood a project will be monitored on-site
20% of monitoring will occur on-site this year

## Slide 5: Project Timeline – Construction Projects
ERR Due: Varies, 60-120 days after award
Plans and Specs Due: 90 days after LOREC/FNORCC
Bid Opening: 45 days after Plans & Specs Approval
Bid Tabs Due: 14 days after Bid Opening
Notice of Contract: 10 days prior to Pre-Construction Conference
Award and PCC
Notice of Start of: After PCC and before construction begins
Construction (Include first HUD-2516 submission)
Project Monitoring: Approximately 50% construction completion
Final Public Hearing: Within 30 days after construction completion
Closeout Due: 15 days after Final Public Hearing
(Closeout will not be approved until final RFP is processed.)

## Slide 6: Project Timeline – Equipment Projects
ERR Due: N/A, submitted with application
Plans and Specs Due: 90 days after LOREC/FNORCC
Bid Opening: 45 days after Plans & Specs Approval
Bid Tabs Due: 14 days after Bid Opening
First HUD-2516 Due: After awarding the bid
Project Monitoring: Delivery of equipment
Final Public Hearing: Within 30 days after equipment delivery
Closeout Due: 15 days after Final Public Hearing
(Closeout will not be approved until final RFP is processed.)

## Slide 7: Environmental Review
ERR Training coming in December
Working on getting some final information from HUD
All acquisition and construction activities, except non-linear infrastructure require a Phase 1 ESA or Transaction Screen
Start early, especially with consultation letters
Ask questions early. An early mistake may result in starting over at the end.
Must receive LOREC and FNORCC to continue

## Slide 8: Invoicing
Invoices should be submitted every 1 to 3 months
Submit to ECD.Invoices@tn.gov
Typically takes two weeks to review and process (if everything is correct)
Double check the previously invoiced amounts; if it gets off, it can cause problems
Invoice templates will come from ecd.tefmsadmin@tn.gov

## Slide 9: Budget Revisions
Submit anytime the budget is adjusted
  Bid Awards
  Change Orders
Must have programmatic approval from CDBG staff for fiscal to approve
Submit to ECD.Invoices@tn.gov

## Slide 10: Fair Housing
All CDBG activities must include a fair housing activity that addresses at least one fair housing impediment
Fair housing activities must be approved by ECD
Do this early, and always before monitoring

## Slide 11: Plans and Specifications
Include all applicable forms, certifications, and affidavits
  Use Exhibit F-1 for construction projects
  Use Exhibit F-5 for equipment projects
  New certification included – Anti-Boycott of Israel
Check for brand names and equivalent language
Water & sewer plans and specs must be sent to TDEC for review
Include ERR consultation LOREC notations

## Slide 12: Plans and Specifications
Equipment with installation cost over 13% need to include Davis-Bacon language
  Rare cases, typically sirens and communication towers
Plans to bid loose equipment as a package, not line item
Be specific about what is required (ie. If equipment is being purchased and installation is needed, be sure it is included in the specs.)
Think of ways to encourage participation from bidders

## Slide 13: Plans and Specifications
Must submit to GoDBE portal
Reminder: Review before submitting to ECD
2023 projects: Make sure to consider BABA iron and steel requirements

## Slide 14: Plans and Specifications – Bid Alternates
Consider bid alternates
  Additive
  Deductive
  Provides flexibility and limits chances of rebidding
Additive Alternates
  Start with a base amount and add items as funding permits
  Clearly specify the order in which items will be added
Deductive Alternates
  Start with a complete project and remove items as needed to bring the project in-line with funding
  Clearly specify the order in which items will be removed
  Be careful to not reduce the scope

## Slide 15: Plans and Specifications
Statewide Contract:
  Documentation of listing on Active Statewide Contract list
  Request letter from mayor
  Submitted to ECD prior to contacting vendor
Cooperative Agreement:
  Request letter from mayor
  Documentation from the other governmental entity or service
  If using a service/platform, documentation the method of procurement is compliant with the State of TN
  Adopted resolution agreeing to the terms of the master agreement of the cooperative purchase service/platform
  Must comply with local procurement policies

## Slide 16: Bidding and Procurement
Bid opening must be advertised in a newspaper
  Does not have to be daily
  Consider other actions to solicit bidders
All addenda must be approved by ECD
  Submit at least 4 days prior to bid opening
  State law requires 48 hours notice to bidders

## Slide 17: Recommendations for Bid Award
If recommendation comes from engineer, letter from mayor must be included
All executed certifications and affidavits from bidder must be included
If local procurement policy requires council/commission approval, minutes must be included
Bid advertisement with date of ad run must be included
Minutes of bid opening must be included

## Slide 18: Recommendations for Bid Award
If low bidder is not selected, justification must be included
If selected bid exceeds budget amount, resolution for additional funding must be included
If only one bidder* submits and you wish to accept the bid, the following must be included:
  Efforts to solicit bids
  Interest from potential bidders
  Justification why rebidding with additional efforts or changes to the plans and specs won’t result in increased competition
* Justification must be compelling.

## Slide 19: Pre-Construction Conference
Notify ECD at least 10 days prior to the Pre-Construction Conference (PCC). Link: Notice of Contract Award and PCC
Clearly explain expectations and requirements to contractors
  Davis-Bacon and Labor Requirements
  Section 3 Requirements
  Change Order Process
  Invoicing Process

## Slide 20: Start of Construction
Submit Notice of Start of Construction to ECD once date is set. Link: Notice of Start of Construction
Include initial Contract/Subcontract Activity Report with Notice of Start of Construction. Link: Form HUD-2516

## Slide 21: Contractor/Subcontractor Report
Contractor/Subcontractor Report
  Submit to Lee Peterson at lee.peterson@tn.gov
  Submit with Notice of Start of Construction or when equipment order is placed
  Submit updated forms anytime a new contractor or sub is included
  Make sure you are using the CPD codes, not housing (1-3)
  Required for all CDBG projects (including equipment)
  Updated copies may be requested at time of monitoring
  Will require a final report with closeout submission

## Slide 22: Contractor/Subcontractor Report
Grant/Project Number 7a.
  5 digit contract number
Amount of Contract or Subcontract 7b.
  Amount of the awarded contracts
  Do not reduce subcontracts from prime
  Do not revise with change orders
Type of Trade Codes 7c.
  1 = New Construction
  2 = Education/Training
  3 = Other (This will include professional services)
Administration and Engineering are prime contracts
Contractor ID = FEIN

## Slide 23: Change Orders
We allow increases work by more than 20% if the attorney provides a letter
  There will still need to be scope changes for a decrease in work of 20% or more
Change orders cannot be used for cost increases, only quantities and time
Justification/explanation from engineer must be included
  Letter of concurrence from mayor included
Adjustments to professional services require approval
  We are still having some trouble here

## Slide 24: Section 3
New Section 3 rule applies to 2021 and later grants
Applies to only to construction projects with HUD assistance over $200,000
Shift from Section 3 hires to Section 3 hours worked
Plan to track Section 3 hours with weekly payrolls
Review new Section 3 chapter

## Slide 25: Section 3
Download the Section 3 Worker Certification form once the awarded bid is contracted
  Income data is updated annually
Section 3 Labor Hours Tracking Form or comparable form must be submitted at closeout
Will be checked at monitoring

## Slide 26: Davis-Bacon and Labor Requirements
Interview employees early in the project to catch problems early
  At least once a month, minimum
Get enough interviews to cover all wage classifications used
Make sure the employee interviews and payrolls match the job classification
Review the first few payrolls CLOSELY and fix the problems early on

## Slide 27: Davis-Bacon and Labor Requirements
Review the first few payrolls CLOSELY and fix the problems early on
All required posters and applicable wage decision must be clearly posted at the job site
  Will result in a finding at monitoring if not

## Slide 28: Additional Wage Classification Requests
Submit requests before work is done, as soon after contracting as you can
DOL at times takes 2-3 months to respond to requests
Things to consider
  Communicate with contractors about reasonableness
  Make sure requests include justification
  Other classifications don’t always work as justification
  If the additional classification is a skill position, use a published skilled rate as a basis; DOL will

## Slide 29: Build America, Buy America (BABA)
BABA requires any “infrastructure project” funded by any “Federal Financial Assistance” (FFA) apply a domestic content procurement preference, meaning that all iron, steel, manufactured products, and construction materials used in the infrastructure project have been produced in the United States, unless the awarding agency has issued a waiver of this requirement.
Implemented differently by each federal funding agency
HUD BABA website

## Slide 30: Build America, Buy America (BABA)
BABA implementation for CDBG is phased
  FY23: Iron and Steel
  FY24: Specifically-listed construction materials:
    non-ferrous metals;
    lumber;
    composite building materials; and
    plastic and polymerbased pipe and tube
  FY25: all other construction materials and manufactured products
Begins with 2023 funded grants

## Slide 31: Build America, Buy America (BABA)
General Waivers
  Small grants – the total project cost is less than $250,000
  De Minimis – a cumulative total of no more than 5% of the total cost of the iron, steel, manufactured products, and construction materials, up to a maximum of $1 million
  Exigent Circumstances – urgent need or a threat to life, safety, or property of residents and the community
Specific Waivers
  Public Interest – the use of the American made product would be inconsistent with the public interest
  Non-Availability – the product needed is not produced in the United States in sufficient quantities or of a satisfactory quality
  Unreasonable Cost – inclusion of the product produced in the US will increase the cost of the overall project by more than 25%

## Slide 32: Build America, Buy America (BABA)
HUD is providing guidance on BABA implementation now
Manual will be updated with information, guidance, and forms soon
Project specific waivers will require review by HUD and the Made in America Office

## Slide 33: Violence Against Women Act (VAWA)
Reauthorization in 2022 included CDBG
Still awaiting clear guidance from HUD
Requirements of CDBG recipients:
  Report on the existence of laws or policies they or their subgrantees (or state grant recipients) adopted that impose penalties based on requests for law enforcement or emergency assistance or based on criminal activity that occurred at a covered property.
  Certify that they and their subgrantees are in compliance or describe the steps they and their subgrantees must take to comply within 180 days of the report to HUD.

## Slide 34: Monitoring
Davis-Bacon is the biggest challenge, pay careful attention here
  Labor findings generally take the longest to resolve
Generally, set at 50% construction completion or equipment delivery
  Make sure enough employee interviews have been conducted
  Make sure Fair Housing activity is complete

## Slide 35: Monitoring
Submit requests for monitoring online
  Link: CDBG Monitoring Form
Webform must be completed and documents submitted at least one week prior to monitoring appointment
  Link: CDBG Electronic Monitoring

## Slide 36: Contract Amendments
Reasons to amend a contract
  Extension of contract period
  Change in scope
  Budget adjustment to zero-dollar line items
Contract Extension
  Request contract extension using the new online form. Select the “Contract Amendment” tab on our Grant Administration page.
  Include the current budget
  Submit at least 60 days prior to contract expiration

## Slide 37: Monthly and Annual Reports
Monthly Status Reports are required to be submitted by the 28th of each month
Annual Reports due at the end of December
Will take the place of the December monthly report
Link: CDBG Annual Report
  Be sure to select Annual Report
Performance measures should match those in application

## Slide 38: Closeouts
Same link as Annual Report, just select Closeout Report
Section 3 is now consolidated into the Closeout report
All open grants must be closed to apply
Closeout public hearings should be held within 30 days of the end of construction
Link: CDBG Closeout Report
  Be sure to select Closeout Report

## Slide 39
Kent Archer
(615) 354-3591
kent.archer@tn.gov